Deviation Management – Estimation

Two months, Monday 7 September to Friday 6 November 2026. 45 working days, weekends excluded, no public holidays deducted. One developer.

# Schedule

| # | Work package | Dates | Days |
| --- | --- | --- | --- |
| 1 | Analysis, design and open points | Mon 07 Sep – Wed 09 Sep | 3 |
| 2 | Health screen: columns, tick box, green row | Thu 10 Sep – Tue 15 Sep | 4 |
| 3 | Filtering law lookup | Wed 16 Sep – Fri 18 Sep | 3 |
| 4 | Persistence: entity, DDL, DTOs, delegate | Mon 21 Sep – Thu 24 Sep | 4 |
| 5 | Save and load wiring, end-to-end test | Fri 25 Sep – Tue 29 Sep | 3 |
| 6 | Three tabs shell | Wed 30 Sep – Thu 01 Oct | 2 |
| 7 | Deviation List tab | Fri 02 Oct – Wed 07 Oct | 4 |
| 8 | Deviation History tab | Thu 08 Oct – Mon 12 Oct | 3 |
| 9 | Manage Filtering Laws dialog | Tue 13 Oct – Mon 19 Oct | 5 |
| 10 | Applicability by session data date | Tue 20 Oct – Fri 23 Oct | 4 |
| 11 | Relearn integration | Mon 26 Oct – Tue 27 Oct | 2 |
| 12 | Configuration update warnings | Wed 28 Oct – Thu 29 Oct | 2 |
| 13 | DACOM extraction | Fri 30 Oct – Mon 02 Nov | 2 |
| 14 | Purge job | Tue 03 Nov – Tue 03 Nov | 1 |
| 15 | Test, fixes and delivery | Wed 04 Nov – Fri 06 Nov | 3 |

# Scope of each package

| # | Work package | What it covers |
| --- | --- | --- |
| 1 | Analysis, design and open points | Walk the threshold read path end to end. Close the blocking questions: baseline reference on acknowledge, relearn on an already-learned threshold, the definition of session data date, and whether GSC_CONFIGURATION.sql is in scope. |
| 2 | Health screen: columns, tick box, green row | Column widths, remove the Activate / Remove tick box, add the Filtering Law and TE columns, green highlight on a deviated row, guidance message, deviated-row guard in canModify. |
| 3 | Filtering law lookup | Force the lazy collection in HealthDao.getLatestConfiguration, add getFilteringLawNames through the business layer, wire the combo editor. Server rebuild and redeploy. |
| 4 | Persistence: entity, DDL, DTOs, delegate | Three columns on THRESHOLD_CONFIGURATION, the migration script, the same fields on both DTOs, and the copy in HealthDelegate.updateHealthConfiguration. |
| 5 | Save and load wiring, end-to-end test | innerSave populates the new DTO fields with the start date round-tripped; HealthCommonBusiness.getThresholds loads them back. First full create, Apply, reopen test. |
| 6 | Three tabs shell | TabFolder on the Health page with Configuration, Deviation list and Deviation history. Existing tree moves into the first tab. |
| 7 | Deviation List tab | Read-only table of active deviations: indicator path, only the modified parameters, filtering law and its contextual parameters, TE, date. Delete with confirmation popup, reset to configuration defaults. |
| 8 | Deviation History tab | Same columns plus the acknowledgment date and a start-to-end range. Component arborescence needs a second parent level on the model. |
| 9 | Manage Filtering Laws dialog | TitleAreaDialog, master-detail, one to five contextual parameters, unique name check, read-only laws greyed and non-selectable, create / update / delete with confirmation. Needs new server methods for law CRUD. |
| 10 | Applicability by session data date | Deviation-aware threshold resolution keyed on the session data date, not the offload date. Highest technical risk; the estimate moves with the number of threshold read call sites. |
| 11 | Relearn integration | Relearn triggered on FIXED to LEARNED and on LEARNED with new bounds, on creation and deletion alike. Confirm a relearn request does not clear the deviation. |
| 12 | Configuration update warnings | Acknowledge every deviation on the SN when a new configuration is applied, with the warning on the Update Aircraft window, the Import configurations dialog and the Threshold learning dialog. |
| 13 | DACOM extraction | New GSC_DEVIATIONS.sql for active deviations only, and the THRESHOLDS flow carrying deviated values with no format change. |
| 14 | Purge job | Delete when the deviation end date is at or before the start date of the oldest non-purged session. |
| 15 | Test, fixes and delivery | Date-applicability matrix, relearn matrix both directions, acknowledge on configuration update, M'ARMS and HELIONIX with EVM indicators included. |

# Milestones

| Date | Milestone |
| --- | --- |
| Tue 15 Sep | Health screen complete on the client, no server change yet |
| Fri 18 Sep | Filtering law dropdown reads the real configuration |
| Tue 29 Sep | Deviation survives Apply and reload – first end-to-end demo |
| Mon 12 Oct | All three tabs functional |
| Mon 19 Oct | Manage Filtering Laws complete – requirement 1 fully delivered |
| Fri 23 Oct | Session-date applicability working (REQ 12) |
| Mon 02 Nov | Extraction to Airbus working (REQ 13) |
| Fri 06 Nov | Delivery |

# What the estimate assumes

One developer, full time, no parallel work. Server rebuild and redeploy available on demand; work packages 3, 4 and 9 each need one. The four blocking questions from package 1 answered within that first week. Test data available for both M'ARMS and HELIONIX, with flights loaded – the current test aircraft has none, which blocks the Apply dialog. GSC_CONFIGURATION.sql treated as out of scope; it is unestimated and would add to package 13.

# Where it is most likely to slip

| Package | Risk | Effect |
| --- | --- | --- |
| 10 – Applicability | The estimate assumes a small number of threshold read call sites that can be routed through one resolver. Count them before committing: grep getThresholdValue, minimumThreshold, getMinValue. | Could double to 8 days |
| 9 – Filtering laws | Law CRUD needs server methods that do not exist yet, and the read-only rule depends on knowing whether any deviation references a law. | +2 days |
| 4 and 5 – Persistence | isEnabled() currently filters saves, and every Apply rebuilds the threshold rows with new ids. Both are known and priced, but either could surface further coupling. | +2 days |
| 8 – Tabs | Component arborescence needs a second parent level the model does not carry today. | +1 day |

Total contingency across the four risks is roughly two weeks. If the estimate has to be a single date with no contingency, 6 November is achievable only if package 10 turns out to be the small version.